## Template
Bits&Bots |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7
Start Date: 07/02/23 | Completion Date 19/03/23 |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
Planning |  | 5 days | bar: WEEK 1 M to WEEK 1 SA
Researching on Project |  | 2 d | bar: WEEK 1 M to WEEK 1 T; WEEK 1 SA
Creating Gant chart |  | 1 d | bar: WEEK 1 W; WEEK 1 SA
Gathering Resources |  | 2 d | bar: WEEK 1 TH to WEEK 1 SA
Design |  | 7 days | bar: WEEK 1 SU to WEEK 2 SU
Designing Prototype XD |  | 3 d | bar: WEEK 1 SU to WEEK 2 T; WEEK 2 SA
Make prototypes |  | 3 d | bar: WEEK 2 SA
Style guide |  | 4 d | bar: WEEK 2 F to WEEK 2 SU
Project sub part-1. | bar: WEEK 2 SA to WEEK 2 SU
Development process |  | 24 d | bar: WEEK 3 M to WEEK 7 T
Coding process |  | 24 d | bar: WEEK 3 M to WEEK 7 T
Testing |  | 4 d | WEEK 4 M: Mar
Testing the Mobile version |  | 2 d | bar: WEEK 7 W
Testing the Desktop version |  | 2 d
Project final submission |  | 1 d | [48 empty] | 19/03/23
Submission of Project |  | 1 d
Annotation |  |  | WEEK 1 SA: Planning
Design
[8 empty] | Develoment process | [10 empty] | Weekend
Testing
Project submission

## Month 1
Project Title... |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4
Start Date: |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
DEVELOPMENT |  | 5 d
Finalize Script | owner | 2 d
Attachments | owner | 3 d
Financing | owner
PRE-PRODUCTION |  | x d
Casting | owner
Set Design | owner
Locations | owner
Costumes | owner
Hair | owner
Make-up | owner
PRODUCTION |  | x d
Rehearsals | owner
Principal Photography | owner
Second Unit | owner
POST-PRODUCTION |  | x d
Editing | owner
VFX | owner
Scoring | owner
Sound Editing | owner
Color Grading | owner
DISTRIBUTION |  | x d
Distribution Deals | owner
Marketing Push | owner
Press Tour | owner
Premieres | owner
ANNOTATIONS |  |  | WEEK 4 TH: Blocked out event
Blocked out phase
[26 empty] | N | Dependency
[26 empty] | n | Dependent Event
#NAME? |  | Modern Production Management Software. Create production calendars, breakdowns, call sheets & more on studiobinder.com | WEEK 4 T: © 2017 - StudioBinder